## OWNER_COCKPIT
Rhea — Owner Cockpit Dashboard (Excel-driven)
North Star | Community-first: grow a small but productive guild; money is a consequence (smart, not fast).
Rule | If it doesn't produce a weekly artifact, it doesn't exist.
Today (manual) | Fill TODAY_CAPSULE + pick 1 artifact to ship.
Quick Links
Master Memo (full context) | Open
Fixator scorecard | Open
Visual schemas | Open
Roadmap backlog | Open
Incidents (Rex 400 etc.) | Open
Decisions | Open
Bias controls | Open
Memory layer options | Open
Exchange protocol with Rex/Office | Open
KPIs (fill weekly)
KPI | Current | Target | Evidence
Artifacts shipped / week |  | Target: 1 | Evidence: PR/Demo link
Onboarding completions / week |  | Target: 3 | Evidence: names + first PR
Active contributors (7d) |  | Target: 5 | Evidence: PR/review count
Decision rollback rate |  | Target: ↓ | Evidence: incident log
Context-loss incidents |  | Target: 0 | Evidence: logs exist

## EXCHANGE_PROTOCOL
Exchange Protocol — Rex ↔ ChatGPT with you as observer
Reality check | Direct model-to-model messaging isn't available here. Use a shared artifact (files) that both sides read/write: git repo, shared folder, or periodic exports you upload here.
Lowest-friction workable loop
Step 1 | Rex writes/updates MASTER_MEMO.md + TODAY_CAPSULE.md + DECISIONS.md + INCIDENTS.md in your repo (or shared folder).
Step 2 | Rex exports a snapshot as XLSX (or zips the md files) and drops it into your Office shared channel.
Step 3 | You (observer) upload the snapshot here (or paste diffs).
Step 4 | I produce an annotated diff + updated cockpit workbook; you pass it back to Rex.
File contract (lossless exchange)
TODAY_CAPSULE.md | Objective / Done / Blockers / Next 3 actions / Stop rule / Timestamp
DECISIONS.md | Immutable decisions with rationale + source pointers
INCIDENTS.md | Errors (400 etc.), mitigations, status
BACKLOG.csv | One row per task: owner, metric, timebox, artifact

## INDEX
Rhea — Master Memo (community-first, automation roadmap)
Scope note | This memo summarizes the content available in this chat/session. If you have older chats elsewhere, export them and I can merge them into the same structure.
Table of contents (click)
Timeline summary | Open
Key decisions & constraints | Open
Product direction: community-first | Open
Architecture options (Dify/LibreChat/vLLM/etc.) | Open
Fixator system (criteria, scorecards, anti-bias) | Open
Continuity playbook (sessions, capsules, logs) | Open
Incident: Rex 400 + terminal history loss | Open
Weaknesses in current approach + countermeasures | Open
Resources & reading list | Open

## TIMELINE
Timeline (chronological, newest → older)
Phase | Theme | Summary (what happened / what changed)
Now | Goal framing | Community-first monetization; 'money smart, not fast'. Need long-horizon system: onboarding, rituals, artifacts.
Earlier | Stack discussion | Rejecting docker stack '3lm+comfy+lobe'. Explored alternatives: API-first fast release; dockerless self-host via systemd; Mac/MLX angle.
Earlier | Dify workflow | Dify nodes often return objects/lists; LLM expects strings. Normalize with a Code node → mem_text.
Earlier | Critique mode | Switched to strict criticism mode: require operational criteria, baselines, measurable 'proof'.
Earlier | Fixators & biases | Built fixator scorecard and bias→control map; multi-model adjudication schema; 'environment beats motivation'.
Earlier | Memory layers | Discussed Mem0-like memory layers; adopt only if you can measure retrieval precision + deletion/forget.
Earlier | Operational pain | Rex agent 400; b-2nd terminal window lost scrollback; fear of reboot and losing context.

## DECISIONS
Key decisions, constraints, and working assumptions
Core goal
Goal | Earn money 'smart, not fast' via community-first approach; product is culture + artifacts, not a feature zoo.
Constraints (non-negotiables)
Constraint #1 | 1-month 'release pressure' is toxic unless scope is brutally small.
Constraint #2 | Avoid building an open-source Frankenstein: ship one usable ritual/artifact loop.
Constraint #3 | Avoid 'trust the algorithm, turn off brain' cult logic: require criteria, stop rules, measurement.
Chosen direction candidates
Candidate A | Community OS first (onboarding + rituals + HF artifacts + gated access).
Candidate B | iOS AI-scheduler MVP as proof of 'environment beats motivation' (contract-of-the-day).
Candidate C | Gateway + billing as infrastructure if/when needed.

## COMMUNITY_OS
Community OS (the product is the community + rituals)
Non-negotiable mechanisms
Mechanism | Status is contribution-based (no 'genius' titles).
Mechanism | Weekly artifact ritual (demo / PR / protocol / postmortem).
Mechanism | Onboarding is intentionally 'boring' and filtering: no access until course + first contribution.
Mechanism | Fork policy: conflict → fork; no endless governance drama.
Minimum viable community launch (30 days)
Deliverable #1 | Landing + manifesto + rules-of-play (1 page each).
Deliverable #2 | One canonical repo 'protocols' (templates, fixators, decision log).
Deliverable #3 | One demo Space / showcase artifact (even if minimal).
Deliverable #4 | Onboarding course (3–5 modules) + automated check + invite code.
Deliverable #5 | Weekly lab call + published changelog.

## ARCHITECTURE
Architecture options (realistic vs fantasy)
Option | Goal | Core components | Why/Tradeoffs | Risk level | Notes
API-first (fastest) | Ship & monetize | LibreChat/Dify UI + your gateway + billing/quota; images via API | Min ops, max shipping speed. Self-hosted = BYOK keys. | Low | Good for 30-day launch
Dockerless self-host | Control | vLLM server + LibreChat/Open WebUI + systemd + reverse proxy | No containers; higher ops cost; security hardening needed. | Med | Only if infra is the product
Workflow-heavy gen media | Studio | Dify orchestrates + image engine (InvokeAI/Comfy) | Only if media pipelines are core revenue. | High | Will eat the schedule

## FIXATORS
Fixator system (criteria → score → ship/kill)
The 10-point instant scorecard
Point | Objective (1 sentence, no metaphors)
Point | Success metric (numeric/binary)
Point | Timebox (<= 1 week / <= 30 min)
Point | Assumptions (<= 3)
Point | Baseline (do-nothing outcome)
Point | Reversibility (rollback)
Point | Cost ceiling (time/tokens/$)
Point | Stop condition (abort rule)
Point | Owner + next action (one verb)
Point | Artifact output (PR/doc/demo/log)
Rule
Decision rule | 8–10 SHIP ¦ 6–7 REWRITE ¦ ≤5 TRASH. No exceptions.

## CONTINUITY
Continuity playbook (avoid losing context across sessions)
Principle
Reality | Treat chat as cache. Treat files + git + logs as truth.
Hardening techniques
Technique #1 | Daily capsule file (<= 500 tokens): today's goal, decisions, next 3 actions.
Technique #2 | DECISIONS.md / INCIDENTS.md / GEMS.md on disk, committed to git.
Technique #3 | Terminal recording for agents: `script` or tmux logging; store under /logs/.
Technique #4 | Never rely on scrollback as storage. Assume it can vanish.
Technique #5 | Checkpoint ritual: every 2–3 hours create a small commit + note.

## INCIDENTS
Incidents & recovery (Rex 400, terminal history loss)
Rex 400 — what it usually means
Meaning | HTTP 400 in Anthropic API = invalid_request_error (request format/content). Different from 429 rate limits or 413 request-too-large.
Debug checklist (do in order)
Step 1 | Capture the exact error payload (copy JSON). 400s are diagnosable only with the message.
Step 2 | Look for malformed tool-use blocks (tool_use without tool_result). This can brick sessions.
Step 3 | Check request size: if huge, reduce context; split tool calls; restart with a capsule.
Step 4 | If it's Claude Code/terminal agent: check local logs/config for corrupt state; try a new session in a new folder.
Terminal history loss — prevention
Problem | Terminal scrollback is not durable. When the window refreshes, you lose it.
Fix | Record sessions with `script` (typescript file) or tmux logging; store in repo /logs/.

## WEAKNESSES
Weaknesses in the current approach (and how to fix them)
Structural weaknesses (blunt)
Weakness | Scope addiction
Why it's bad | Trying to ship 'everything' (platform) instead of one ritual that sells.
Countermeasure | Force 7-day shipping loop; ban feature sprawl.
Weakness | Unmeasured superiority claims
Why it's bad | 'Faster and more accurate than all' without baseline is self-hypnosis.
Countermeasure | Define 20-task benchmark; log success rate + time.
Weakness | Myth-driven governance
Why it's bad | 'Elite freaks' framing kills growth; status games.
Countermeasure | Contribution-only access + artifacts per week.
Weakness | Reliance on volatile context
Why it's bad | Depending on chat/scrollback for state creates fear and paralysis.
Countermeasure | Capsule + git + logs; treat chat as cache.

## RESOURCES
Resources (learning materials)
Agent errors & reliability
Anthropic API errors (400/413/429 etc.) | https://docs.anthropic.com/en/api/errors
Claude Code issue example: invalid request bricking a session | https://github.com/anthropics/claude-code/issues/679
Recording terminal sessions: `script` overview | https://en.wikipedia.org/wiki/Script_(Unix)
How to use `script` in practice (guide) | https://www.linux.com/news/how-to-capture-terminal-sessions-and-output-with-the-linux-script-command/
AI memory layers (Mem0-like)
Mem0 overview | https://mem0.ai/
Mem0 platform docs | https://docs.mem0.ai/platform/overview
Letta (MemGPT lineage) architecture | https://docs.letta.com/guides/agents/architectures/memgpt
Memlayer (OSS memory layer) | https://github.com/divagr18/memlayer

## Schemas
Editable Schemas (copy/paste into docs or adapt for your team)
Schema 1 — Fixator Decision Loop
| Fixator (Goal + Metric + Stop) |  |  | Execute (Small batch) |  | Measure (Logs + Cost) |  | Postmortem (Update rules)
|  |  | → |  | → |  | →
↺
Schema 2 — Multi-model Adjudication (Critics + Aggregator + Veto)
Critic A (Risks)
| Proposer (Plan/Template) |  |  |  |  | Aggregator (Score + Summarize) |  | Decision Ship / Rewrite / Trash
|  |  | → | Critic B (Missing assumptions) | → |  | →
Critic C (Cost/Time)
Rule: no aggregation without explicit STOP condition.
Schema 3 — Memory Layer in Agent Stack (Mem0-like)
Memory KV
| App UI (Web/iOS) |  |  | Orchestrator (Workflow/Tools) |  |  |  | LLM + Tools (Search, Code, etc.)
|  |  | → |  | → | Memory Vector | →
Memory Graph
Use memory only when you can measure retrieval precision and allow deletion/forget.
Schema 4 — Environment > Motivation (Stability Engineering)
| Constraints (Default paths) |  |  | Rituals (Weekly artifacts) |  | Instrumentation (Metrics/logs) |  | Governance (Veto/Rules)
|  |  | → |  | → |  | →
If you can't measure it, it can't enter the queue.

## Fixator_Scorecard
Fixator Template — Instant Scorecard
Paste your proposed fixator template below. Fill the right-hand checks (0/1). Score updates automatically.
Proposed fixator (raw text) | (Paste here)
Checklist (each = 1 point)
Item | Definition | Pass (0/1) | Weight | Points
Objective | One sentence objective (no metaphors) | 0 | 1
Success metric | One numeric or binary success metric | 0 | 1
Timebox | Explicit timebox (<= 1 week / <= 30 min) | 0 | 1
Assumptions | Max 3 assumptions stated | 0 | 1
Baseline | What happens if we do nothing | 0 | 1
Reversibility | How to undo / rollback | 0 | 1
Cost ceiling | Max cost/time/tokens | 0 | 1
Stop condition | Explicit abort rule | 0 | 1
Owner+Next | One owner + one next action verb | 0 | 1
Artifact output | PR / doc / demo / log produced | 0 | 1
Total Score
Decision | 8–10 = SHIP ¦ 6–7 = REWRITE ¦ ≤5 = TRASH

## Roadmap
Automation Roadmap — extend basics into professional spheres
Each row is a ready backlog item. Copy into your tracker. Keep batches small; measure everything.
Sphere | Job-to-be-done | Automation candidate | Inputs needed | Risks/Failure modes | Fixator template type | Success metric | Timebox | Default tools | Notes/Links
Product/Engineering | Turn idea into shipped artifact | Weekly shipping loop (PR + demo) | Backlog, repo, CI | Scope creep; no stop rule | Ship/Rewrite/Trash scorecard | 1 shipped artifact/week | 7 days | GitHub, CI, issue tracker | Use Schema 1
Product/Engineering | Spec decisions | Fixator decision gate for every change | Fixator doc | Ambiguous goals | Decision fixator | Decision rollback rate ↓ | 30 min | Docs, templates | Score >=8 required
Research | Evaluate approach | Baseline vs candidate benchmark | Task set, rubric | Cherry-picking tasks | Benchmark fixator | Success rate ≥80% | 1–2 days | Notebook, eval harness | Log failures
Writing/Media | Publish regularly | Weekly artifact publishing pipeline | Drafts, sources | Perfectionism, endless edits | Artifact fixator | 1 publish/week | 7 days | Docs, CMS | Timebox hard
Ops/Admin | Boring tasks | Auto-triage + checklists | Email, calendar | Over-automation | Checklist fixator | SLA met | 1 day | Zapier/Make | Kill switch
Sales/Support | Answer with context | Memory-backed support agent | Past tickets, KB | Wrong memory retrieved | Memory policy fixator | CSAT ↑; repeats ↓ | 2 days | Mem0/Letta + KB | Must allow deletion
HR/People | Onboard members | Onboarding course + first contribution | Docs, repo | Status games | Contribution fixator | First PR within 72h | 1 week | LMS, GitHub | No PR, no access
Personal productivity | Maintain focus | Daily contract + review loop | Tasks, calendar | Shame loops | Contract fixator | Streak days | 1 day | iOS app | Environment > motivation

## Bias_Controls
Bias → Control Pattern Map (use 1 control per decision, not 50)
Goal: bound error, not eliminate bias. Add controls into fixator templates.
Bias/Failure mode | Symptom | Control pattern | Fixator field to add | Measurement | Stop rule example | Notes
Confirmation bias | Only seeing supporting evidence | Forced counter-evidence: '3 strongest disconfirmations' | Assumptions + Counter-evidence | # of disconfirmations logged | STOP if no counter-evidence found
Availability heuristic | Overweight vivid recent events | Use base rates / historical logs | Baseline + Prior | Variance vs historical | STOP if decision deviates >2σ
Sunk cost | Keep investing because invested | Reversibility + cost ceiling + kill switch | Cost ceiling + Stop condition | % projects killed early | STOP if ceiling exceeded
Planning fallacy | Underestimate time | Timebox + small batch + weekly shipping | Timebox | Schedule slip rate | STOP if slip > 1 timebox
Authority bias | Overweight 'strong model' / leader | Adversarial critic required | Adversarial check | # critic issues found | STOP if critic flags irreversible risk
Goodhart's law | Metric gaming | Multiple metrics + manual audit sample | Success metric + Audit | Audit failure rate | STOP if audit fails
Overconfidence | No error bars | Confidence interval + pre-mortem | Pre-mortem | Calibration score | STOP if confidence uncalibrated

## Memory_Layers
Mem0-like options (memory layer / long-term context) — quick comparison
These are not magic. Adopt only if you can measure retrieval precision and support deletion/forget.
Name | Type | Deploy | Core idea | Strengths | Risks | Link
Mem0 | Memory layer | Hosted + OSS | Compress/store/recall memories; observability | Fast integration; tracing; token savings claims | Wrong memory retrieval; privacy; stale memories | https://mem0.ai/
Mem0 OpenMemory | MCP memory | Local/hosted | Project-scoped memory for coding agents via MCP | Tool-agnostic; editable memories | Leakage if misconfigured; memory bloat | https://mem0.ai/openmemory
Letta (MemGPT lineage) | Agent framework | OSS + commercial | Memory hierarchy (core + archival) for agents | Explicit memory classes; context engineering | Complexity; needs discipline | https://docs.letta.com/guides/agents/architectures/memgpt
Memlayer | Memory layer | OSS | Plug-and-play persistent memory; multi-tier retrieval | Local-first claims; fast search | Immature; evaluation burden | https://github.com/divagr18/memlayer
MemoAIr | Unified context layer | Commercial | Graph-based unified memory across tools | Org + user + domain layers (per claim) | Marketing claims; lock-in | https://memoair.space/

## Sources
Sources (URLs)
https://mem0.ai/
https://github.com/mem0ai/mem0
https://docs.mem0.ai/platform/overview
https://mem0.ai/openmemory
https://www.letta.com/blog/memgpt-and-letta
https://docs.letta.com/guides/agents/architectures/memgpt
https://github.com/divagr18/memlayer
https://memoair.space/

## README
What this workbook is
Use it as a core roadmap for general automation: fixator templates, decision loops, memory-layer options (Mem0-like), and measurable outcomes.
How to use (fast)
Step 1 | 1) Go to Fixator_Scorecard: paste any proposed 'fixator template' and score it in <60 seconds.
Step 2 | 2) If score < 8, rewrite until it passes (or trash it).
Step 3 | 3) Go to Roadmap: pick your professional sphere and copy a ready automation backlog.
Step 4 | 4) If you need long-term context, compare memory layers in Memory_Layers and pick one.
Step 5 | 5) Use Bias_Controls to add one bias guardrail per decision, not fifty.
Visual Schemas | See Schemas sheet for 4 ready-to-use process diagrams (cell-based, editable).

## LIMITATIONS
Limitations & Required Inputs
I can't | Read your local terminal scrollback, access your Office docs, or message Rex directly. I only see what you paste/upload here.
To minimize your mediation | Make Rex generate a single MASTER_MEMO + capsule files and export them (XLSX/ZIP) for you to upload. Then I can iterate without you digging through dozens of dialogs.